## 00_API_Product_Management_Test_
Build Version | V-1.0
Module Name | API Product Management
Created By | James Ian Largo
Date of Creation | 2026-03-12
Test Run ID | Test Case ID | API Test Scenario ID | Test Steps | Test Data | Executed By | Date | Environment | Status | Actual Result | Defect ID / Remarks
TR-001 | TC-001 | API-TS-001 | Send POST request with valid payload | TD-001 | James Ian Largo | 2026-03-12 | QA | Pass | 201 Created, food record successfully saved in database | N/A
TR-002 | TC-002 | API-TS-002 | Submit request with missing required field | TD-002 | James Ian Largo | 2026-03-12 | QA | Fail | 400 Bad Request returned with validation error message | DEF-001
TR-003 | TC-003 | API-TS-003 | Submit incorrect price data type | TD-003 | James Ian Largo | 2026-03-12 | QA | Fail | 201 Created returned, API accepted invalid price data type | 1. DEF-002 2. Data type validation for price not implemented
TR-004 | TC-004 | API-TS-004 | Submit field below minimum length | TD-004 | James Ian Largo | 2026-03-12 | QA | Fail | 201 Created returned, API accepted input below minimum length | 1. DEF-003 2. Boundary validation missing
TR-005 | TC-005 | API-TS-005 | Send GET request | TD-005 | James Ian Largo | 2026-03-12 | QA | Pass | 200 OK returned with list of food products | N/A
TR-006 | TC-006 | API-TS-006 | Request food by ID | TD-006 | James Ian Largo | 2026-03-12 | QA | Fail | Returned with all the products | DEF-004
TR-007 | TC-007 | API-TS-007 | Request non-existing ID | TD-007 | James Ian Largo | 2026-03-12 | QA | Fail | 404 Not Found returned for non-existent food ID | DEF-005
TR-008 | TC-008 | API-TS-008 | Send PUT request to update food | TD-008 | James Ian Largo | 2026-03-12 | QA | Pass | 200 OK returned, food record updated successfully | N/A
TR-009 | TC-009 | API-TS-009 | Submit invalid update payload | TD-009 | James Ian Largo | 2026-03-12 | QA | Fail | 200 OK returned, API updated record despite invalid payload | Update validation missing
TR-010 | TC-010 | API-TS-010 | Send DELETE request | TD-010 | James Ian Largo | 2026-03-12 | QA | Pass | 204 No Content returned, food record deleted successfully | N/A
TR-011 | TC-011 | API-TS-011 | Send SQL injection payload | TD-011 | James Ian Largo | 2026-03-12 | QA | Pass | API accepted payload but stored input as plain text without executing SQL | Input not sanitized but database safe
TR-012 | TC-012 | API-TS-012 | Send unsupported HTTP method | TD-012 | James Ian Largo | 2026-03-12 | QA | Fail | 200 OK returned instead of 405 Method Not Allowed | 1. DEF-007 2. HTTP method restriction missing
TR-013 | TC-013 | API-TS-013 | Send invalid Content-Type header | TD-013 | James Ian Largo | 2026-03-12 | QA | Fail | 201 Created returned, API accepted unsupported Content-Type | 1. DEF-008 2.Content-Type validation missing
TR-014 | TC-014 | API-TS-014 | Measure API response time | TD-014 | James Ian Largo | 2026-03-12 | QA | Pass | Response time measured at 320 ms (< 2 seconds threshold) | Performance within acceptable limit