## Test Plan
Project Overview | This project focuses on building a high-performance, full-stack food delivery ecosystem. The application bridges the gap between hungry users and local eateries through a seamless, real-time ordering experience.
Project Name | Eyan Food Cafe
Build | V- 1.0
Test Manager | James Ian Largo
Date of Creation | 2026-02-22
Test Plan ID | Scope | Objectives | Test Items | Test Documentation Flow | Test Strategy | Test Environment Setup | Risk/Assumptions | Risk/Mitigation | Entry Criteria | Exit Criteria | Responsible person
TP_001 | In – Scope Features: User registration and login • Verify that the user can register and login. Food browsing and search • Ensure that user can browse food products and apply filters and use search functionalities Shopping cart management • (CRUD Operations) Out – Scope: • Payment gateway integration (future release) • Admin panel features | 1. Verify all in-scope features work as expected. 2. Ensure application handles edge cases and invalid input. 3. Identify and document defects. | 1. User Registration & Login 2. Food Browsing and Search 3. Shopping Cart CRUD Operations | Before Testing: • Test Plan document • Detailed Test Cases with steps and expected results • Test Data (valid and invalid). During Testing: • Execution Logs (Pass/Fail) • Defect Reports (with steps, screenshots, severity) • Daily/Weekly Status Reports (progress, open defects, risks) After Testing: • Final Test Report (coverage, defect trends, recommendations) • Defect Log (status: open/fixed/closed) • Test Closure Report (confirmation of release readiness) | Functional testing. • Validate all core workflows: sign up, login, food browsing, search, cart CRUD. • Include boundary tests (e.g., product name max length, cart quantity limits, invalid email/password). Manual Testing. • Focus on edge cases: blank inputs, invalid formats, extremely long inputs, invalid price or product name. Automation Testing. • Playwright scripts for repetitive scenarios: login/logout, cart operations, search. • Regression testing for new builds. API testing. • Verify endpoints respond correctly with both valid and invalid inputs. • Validate status codes, messages, and data integrity. | 1. Server & Database configured to mirror production schema. 2. Install NodeJS/Express for Back-end. 3. Install Playwright for automation. 4. Prepare test data: valid and invalid scenarios. 5. Browsers: Chrome, Firefox on Windows OS. | 1. Unstable Build: Early builds may crash or load modules incorrectly. 2. Validation Requirements: System must display proper error messages. 3. API vs FrontEnd: Ensure API rejects invalid requests even if FrontEnd fails. | 1. Smoke test critical features before full execution 2. Boundary & negative testing 3. Ensure Back-End rejects invalid requests even if FrontEnd fails | 1. Build deployed on test environment. 2. Requirements approved. 3. Test cases and test data prepared. | 1. All planned test cases executed. 2. Critical defects fixed and verified. 3. Test closure report completed. | QA Engineer